## Sheet1
Project Schedule
Daily Express Puzzles

Submitted Date	Detail	Responsible Person
01/18/11	Project Start	---
01/19/11	Option and PuzzleSelect UI finish	Chaichat Athiwarakun
01/20/11	Option and PuzzleSelect Logic finish	Chaichat Athiwarakun
01/21/11	Menu UI finish	Chaichat Athiwarakun
01/24/11	Menu Logic finish	Chaichat Athiwarakun
01/25/11	Number Crunch UI finish	Chaichat Athiwarakun
01/26/11	Number Crunch file parse	Chaichat Athiwarakun