## Sheet1
Project Schedule
Daily Express Puzzles

Submitted Date	Detail	Responsible Person
18/01/11	Project Start	---
19/01/11	Option and PuzzleSelect UI finish	Chaichat Athiwarakun
20/01/11	Option and PuzzleSelect Logic finish	Chaichat Athiwarakun
21/01/11	Menu UI finish	Chaichat Athiwarakun
24/01/11	Menu Logic finish	Chaichat Athiwarakun
25/01/11	Number Crunch UI finish	Chaichat Athiwarakun
26/01/11	Number Crunch file parse	Chaichat Athiwarakun